|  | Goals and Objectives | Individual(s) Responsible | Resources Needed | Action Taken/Status | Projected Start Date | Target Date for Completion | Progress Review Date (if needed) | Funding Date | Dean’s Support |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Support the Maintenance of CACREP Accreditation and Transition to 2024 Standards |  |  |  |  |  |  |  |  |  |
|  | a. Update all programs to comply with 2024 standards. | COE Dean, Chair, Dept. Faculty | 2 Course Releases (1 Fall, 1 Spring) for Faculty Member to Coordinate Transition One doctoral level GRA (1 Fall, 1 Spring) to support evaluation systems transition | Faculty will begin to review and align course offerings with 2024 standards. | August 2024 | May 2027 | December 2026 |  |  |
|  | b. Update Student Outcome Monitoring System (LiveText) |  |  |  |  |  |  |  |  |
|  | c. Restore department to full clerical assistance per CACREP standards. | Provost, COE Dean | Funding for full time clerical assistance. | Request 1 full time position for Fall 2023. | TBD | December 2023 | December 2023 |  |  |
|  | d. Restore department to 12 Full-Time Faculty Members: Add 3 Faculty Lines (1 in CRC, 1 in SCH, 1 in CMHC) | Provost, COE Dean | Funding for faculty lines plus startup funds. | Request 3 Tenure-track Line for Fall 2024. Continue post-doctoral line | August 2023 | December 2023 | April 2024 |  |  |
| 2. Support High Research Productivity |  |  |  |  |  |  |  |  |  |
|  | a. Tap into the various health-related initiatives: Integrate with FAU I-HEALTH and I-SENSE and research institutes to | COE Dean, Chair, Dept. Faculty | Funding for faculty lines plus startup funds. | Request 3 Tenure-track Line for Fall 2024. | Ongoing | Ongoing | August 2025 |  |  |

|  | leverage training of counseling students working in integrated medical practices. a. |  |  | Continue post-doctoral line |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | b. Additional pre- and post-award grant support/ Explore and/or work with the Division of Research to determine how to recoup a greater share of those (grant) funds | VP of Research, COE Dean, Associate Dean | Clarify COE policy on IDC sharing, and faculty incentives for grant writing | VPR has initiated a task force to investigate. 15% of IDC to the colleges and are recommending that 5% of this money goes back to the PI's directly. | Ongoing | Ongoing | August 2025 |  |  |
|  | c. Restore department to 12 Full-Time Faculty Members: Add 3 Faculty Lines (1 in CRC, 1 in SCH, 1 in CMHC) | Provost, COE Dean | Funding for faculty lines plus startup funds. | Request 3 Tenure-track Line for Fall 2024. Continue post- doctoral line | August 2023 | December 2023 | April 2024 |  |  |
|  | d. Restore department to full clerical assistance per CACREP standards. | Provost, COE Dean | Funding for full time clerical assistance. | Request 1 full time position for Fall 2023. | Already begun | December 2023 | December 2023 |  |  |
|  | e. Professional Development/Discretionary funding | Provost, COE Dean | Support Faculty Travel and Expenses to Receive Training. | CE Auxiliary account established. | August 2024 | TBD. | August 2025 |  |  |

| 3. Support High Quality Training |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | a. Re-Constitute Training Clinic and/or provide support for a tele-mental health clinic. | Graduate Dean, COE Dean, Chair, Dept. Faculty | Space for Training Clinic. Support for Clinic Personnel (faculty time, graduate student assistantships) | Space within COE explored. Grant related to tele-mental health explored. | TBD. | TBD. |  |  |  |
|  | b. Funding for recruitment of doctoral students | Provost, COE Dean, Graduate College Dean | Additional recruitment funds and stipends. | ?? | In progress | August 2023 | December 2023 |  |  |
|  | c. Restore department to full clerical assistance per CACREP standards. | Provost, COE Dean | Funding for full time clerical assistance. | Request 1 full time position for Fall 2023. | TBD | December 2023 | December 2023 |  |  |
|  | d. Restore department to 12 Full-Time Faculty Members/ Add 3 Faculty Lines (1 in CRC, 1 in SCH, 1 in CMHC) | Provost, COE Dean | Funding for faculty lines plus startup funds. | Request 3 Tenure-track Line for Fall 2024. Continue post- doctoral line | August 2023 | December 2023 | April 2024 |  |  |
|  | e. Additional pre- and post-award grant support/ Explore and/or work with the Division of Research to determine how to recoup a greater share of those (grant) funds | VP of Research, COE Dean, Associate Dean | Clarify COE policy on IDC sharing, and faculty incentives for grant writing | VPR has initiated a task force to investigate. 15% of IDC to the colleges and are | In progress. | TBD. |  |  |  |

|  |  |  |  | recommending that 5% of this money goes back to the PI's directly. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | f. Develop a comprehensive strategic plan | Provost, COE Dean, CE faculty | Funding for faculty lines plus startup funds. | None to date. | August 2017 | August 2021 | August 2019 |  |  |
| 4. Support Faculty Involvement in University Strategic Plan |  |  |  |  |  |  |  |  |  |
|  | a. Restore department to full clerical assistance per CACREP standards. | Provost, COE Dean | Funding for full time clerical assistance. | Request 1 full time position for Fall 2023. | TBD | December 2023 | December 2023 |  |  |
|  | b. Additional pre- and post-award grant support/ Explore and/or work with the Division of Research to determine how to recoup a greater share of those (grant) funds | VP of Research, COE Dean, Associate Dean | Clarify COE policy on IDC sharing, and faculty incentives for grant writing | VPR has initiated a task force to investigate. 15% of IDC to the colleges and are recommending that 5% of this money goes back to the PI's directly. | In progress. | TBD. |  |  |  |
|  | c. Professional Development/Discretionary funding | Provost, COE Dean | Support Faculty Travel and Expenses to Receive Training. | CE Auxiliary account established. | August 2024 | TBD. |  |  |  |

|  | d. Restore department to 12 Full-Time Faculty Members/ Add 3 Faculty Lines (1 in CRC, 1 in SCH, 1 in CMHC) | Provost, COE Dean | Funding for faculty lines plus startup funds. | Request 3 Tenure-track Line for Fall 2024. Continue post- doctoral line | August 2023 | December 2023 | April 2024 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | e. Tap into the various health-related initiatives: Integrate with FAU I-HEALTH and I-SENSE and research institutes to leverage training of counseling students working in integrated medical practices. | COE Dean, Chair, Dept. Faculty | Funding for faculty lines plus startup funds. | Request 3 Tenure-track Line for Fall 2024. Continue post-doctoral line | Ongoing | Ongoing | August 2025 |  |  |
| 5. Support Department Faculty Leadership and Program Visibility in the Counseling Field |  |  |  |  |  |  |  |  |  |
|  | a. Additional pre- and post-award grant support/ Explore and/or work with the Division of Research to determine how to recoup a greater share of those (grant) funds | VP of Research, COE Dean, Associate Dean | Clarify COE policy on IDC sharing, and faculty incentives for grant writing | VPR has initiated a task force to investigate. 15% of IDC to the colleges and are recommending that 5% of this money goes back to the PI's directly. | In progress. | TBD. |  |  |  |

|  | a. Professional Development/Discretionary funding | Provost, COE Dean | Support Faculty Travel and Expenses to Receive Training. | CE Auxiliary account established. | August 2024 | TBD. |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | b. Tap into the various health-related initiatives: Integrate with FAU I-HEALTH and I-SENSE and research institutes to leverage training of counseling students working in integrated medical practices. | COE Dean, Chair, Dept. Faculty | Funding for faculty lines plus startup funds. | Request 3 Tenure-track Line for Fall 2024. Continue post-doctoral line | Ongoing | Ongoing | August 2025 |  |  |
|  | c. Develop a comprehensive strategic plan | Provost, COE Dean, CE faculty | Funding for faculty lines plus startup funds. | None to date. | August 2017 | August 2021 | August 2019 |  |  |

# Crosswalk to Goals 1-6 to the Site Team report:

B. Weaknesses

1. Doctoral-level Statistics Course within Program (not addressed)

- Clerical support (Goals #1, 2, 3, 4).

- Funding for recruitment of doctoral students (Goal #3).

- Need for additional pre- and post-award grant support (Goals # 2, 4, 5).

- Discretionary funding for travel to conferences, software, and related uses above and beyond current levels (Goals # 2, 4, 5).

- Lack of course/program diversification (not addressed).

C. Recommendations

- Determine the best way to tap into the various health-related initiatives (Goals 2, 4, 5).

- Additional faculty lines would enable them to meet the current and future mental health needs of the region and state (Goals, #1-4).

- Explore and/or work with the Division of Research to determine how to recoup a greater share of those (grant) funds (Goals #2, 3, 4, 5).

- Develop a comprehensive strategic plan (Goals # 1, 2, 4)